## 1_Executive_Summary
GVIAL BHOGAPURAM — PHASE-1 MANPOWER ANALYSIS REPORT
Prepared for Team Lead ¦ Comparison: Phase-1 Immediate (172) vs Full Plan (281) ¦ Generated: 11-Jul-2026
A. HEADLINE NUMBERS
Metric | Value | % | Meaning
Full Client Requirement (Plan 281) | 281 | 100% | CLR Quotation / Consolidated full manpower
Phase-1 Immediate Requirement (172) | 172 | 61% | Ph-1 proposal — deploy now
Deferred beyond Phase-1 (281 − 172) | 109 | 39% | To be planned in later phases
People in Daily Manpower Sheet | 159 | 57% of 281 | Shortlisted / on rolls (Deployed + Will Join)
└ Currently Deployed at Site | 141 | 50% of 281 | Already working on site
└ Will Join (pipeline) | 18 | 6% of 281 | Offer/joining pending
Gap vs Full Plan 281 (281 − 159) | 122 | 43% | Still to hire / fill for full plan
Phase-1 Roster Slots (172) | 172 | 100% of Ph-1 | Base roster positions created
Phase-1 Slots Named / Filled | 91 | 53% of 172 | Name assigned in Deployment172
Phase-1 Slots Still Vacant | 81 | 47% of 172 | Designation kept; Name/Phone empty
B. VERDICT FOR TL (ONE PARAGRAPH)
Phase-1 needs 172 people immediately against a full plan of 281 (109 deferred). Against the full 281 plan we currently have 159 people in the manpower list (141 deployed + 18 will join), leaving a 122-person gap to full plan. Against the Phase-1 172 roster, 91 slots are named (53%) and 81 slots remain vacant (47%). Biggest Phase-1 risks: ELV/SCADA is 0/10 filled; Admin leadership still missing Sr Managers / HSE / Materials; Mechanical has the largest vacant block. Against full 281, largest hiring gaps are Runway Team (−13), HVAC Technicians (−10), Civil Helpers (−8), Pump Operators (−8), and Electrical Shift Engineers (−7).
C. SECTION SNAPSHOT — PHASE-1 (172)
Section | Required (172) | Filled (named) | Vacant | Fill % | Status
ADMIN | 8 | 3 | 5 | 38% | Low
CIVIL | 9 | 9 | 0 | 100% | Complete
ELV / SCADA | 10 | 0 | 10 | 0% | Critical
ELECTRICAL | 46 | 31 | 15 | 67% | On Track
MECHANICAL | 89 | 44 | 45 | 49% | Low
TRANSPORT | 10 | 4 | 6 | 40% | Low
TOTAL | 172 | 91 | 81 | 53% | —
D. TEAM SNAPSHOT — FULL PLAN (281) vs CURRENT FILLED (DailySheet / DesignationSummary)
Team | Description | Required (281) | Filled Now | Gap | Fill % | Priority
A | Site Management Team | 8 | 3 | 5 | 38% | MEDIUM
B | SCADA & Helpdesk Team | 8 | 2 | 6 | 25% | MEDIUM
C | Mechanical & HVAC Team | 56 | 33 | 23 | 59% | HIGH
D | Electrical Team | 71 | 50 | 21 | 70% | HIGH
E | Fire Team | 17 | 14 | 3 | 81% | LOW
F | Civil Team | 92 | 41 | 51 | 45% | HIGH
G | Motor Transport | 18 | 14 | 4 | 78% | LOW
H | Landside Facilities | 11 | 2 | 9 | 18% | MEDIUM
TOTAL |  | 281 | 159 | 122 | 57%

## 2_172_vs_281_Comparison
PHASE-1 (172) vs FULL REQUIREMENT (281) — STRUCTURE COMPARISON
Shows how the immediate Phase-1 ask sits inside the full CLR manpower plan.
Side-by-Side Totals
Bucket | Phase-1 (172) | Full Plan (281) | Difference (absolute / positive) | Notes
Site Management / Admin | 8 | 8 | 0 | Same headcount in Ph-1 and full plan
SCADA / ELV / Helpdesk | 10 | 8 | 2 | Ph-1 ELV scope (10) vs Plan B SCADA+Helpdesk (8) — naming differs; ELV floor techs are Ph-1 specific ¦ Shown as positive Ph-1 excess vs 281 grouping.
Mechanical & HVAC (+ related Ph-1 mech) | 89 | 56 | 33 | Ph-1 Mechanical 89 includes plumbing/pump/sewer/WTP items that sit under Civil (F) in 281 plan ¦ Shown as positive Ph-1 excess vs 281 grouping.
Electrical | 46 | 71 | 25 | 25 electrical roles deferred beyond Phase-1
Fire Team | 0 | 17 | 17 | Fire not in Ph-1 172 proposal total — appears in full 281
Civil (incl. runway/plumber/stores in 281) | 9 | 92 | 83 | Only 9 civil in Ph-1; runway/painter/helpers mostly deferred
Motor Transport | 10 | 18 | 8 | 8 TMT roles deferred
Landside Facilities | 0 | 11 | 11 | Landside not in Ph-1 immediate (all 0 in plan172)
TOTAL | 172 | 281 | 109 | 109 positions are beyond Phase-1 immediate scope
Key Insight
The 172 and 281 sheets use slightly different designation groupings. Ph-1 Mechanical (89) is broader than Plan281 Mechanical team (56) because Ph-1 folds in plumbing, pumps, sewer, WTP/STP and some utility roles that appear under Civil Team (F) in the 281 plan. Fire (17) and Landside (11) are in the full plan but not in the Ph-1 172 immediate proposal. Net deferred = 109 (281 − 172).
What to report to TL
1. Ask client confirmation that Phase-1 go-live target is 172 (not full 281).
2. Treat 109 as deferred backlog — do not mix into Phase-1 daily roster pressure.
3. Focus hiring this week on the 81 vacant Phase-1 slots (especially ELV 10 and Mechanical vacancies).
4. Separately track the 122 gap to full 281 for commercial/manpower planning.

## 3_Designation_Gap_vs_281
DESIGNATION-WISE GAP ANALYSIS vs FULL PLAN (281)
Source: GMR_SUMMARY_MANPOWERSHEET → DesignationSummary + DailySheet (Filled Count = 159)
# | Designation | Team | Required (281) | Filled Now | Shortfall | Surplus | Status
1 | Runway Team | F | 15 | 2 | 13 | 0 | SHORTFALL
2 | HVAC Technician Mechanical | C | 21 | 11 | 10 | 0 | SHORTFALL
3 | Civil Helper | F | 13 | 5 | 8 | 0 | SHORTFALL
4 | Pump Operator | F | 9 | 1 | 8 | 0 | SHORTFALL
5 | Shift Engineer (Electrical) | D | 8 | 1 | 7 | 0 | SHORTFALL
6 | Sewerman & Drainage | F | 6 | 0 | 6 | 0 | SHORTFALL
7 | Sr. Technician Ops | D | 11 | 6 | 5 | 0 | SHORTFALL
8 | Desk Engineer (SCADA) | B | 4 | 0 | 4 | 0 | SHORTFALL
9 | MST | D | 4 | 0 | 4 | 0 | SHORTFALL
10 | Supervisor Civil | F | 7 | 3 | 4 | 0 | SHORTFALL
11 | Mason | F | 5 | 1 | 4 | 0 | SHORTFALL
12 | Electrician L | H | 4 | 0 | 4 | 0 | SHORTFALL
13 | Sr Technician (Mechanical) | C | 4 | 1 | 3 | 0 | SHORTFALL
14 | Help Desk Executive | B | 4 | 2 | 2 | 0 | SHORTFALL
15 | Shift Engineer (Mechanical) | C | 4 | 2 | 2 | 0 | SHORTFALL
16 | PM Technician HVAC | C | 2 | 0 | 2 | 0 | SHORTFALL
17 | Electrician - Ops | D | 28 | 26 | 2 | 0 | SHORTFALL
18 | Tech Associate Electrical | D | 14 | 12 | 2 | 0 | SHORTFALL
19 | Electrician PM | D | 2 | 0 | 2 | 0 | SHORTFALL
20 | Safety Officer | E | 2 | 0 | 2 | 0 | SHORTFALL
21 | Civil Engineer | F | 4 | 2 | 2 | 0 | SHORTFALL
22 | Carpenter | F | 5 | 3 | 2 | 0 | SHORTFALL
23 | Plumber | F | 14 | 12 | 2 | 0 | SHORTFALL
24 | Motor Electrician | G | 2 | 0 | 2 | 0 | SHORTFALL
25 | Tyre Technician | G | 2 | 0 | 2 | 0 | SHORTFALL
26 | Supervisor / Engineer (Landside) | H | 2 | 0 | 2 | 0 | SHORTFALL
27 | Sewerman & Drainage L | H | 2 | 0 | 2 | 0 | SHORTFALL
28 | Helper L | H | 3 | 1 | 2 | 0 | SHORTFALL
29 | Sr. Manager (Mechanical) | A | 1 | 0 | 1 | 0 | SHORTFALL
30 | Sr. Manager (Electrical) | A | 1 | 0 | 1 | 0 | SHORTFALL
31 | Sr. Manager (Civil) | A | 1 | 0 | 1 | 0 | SHORTFALL
32 | HSE & Compliance Manager | A | 1 | 0 | 1 | 0 | SHORTFALL
33 | Materials Manager | A | 1 | 0 | 1 | 0 | SHORTFALL
34 | Asst. Manager (Mechanical) | C | 1 | 0 | 1 | 0 | SHORTFALL
35 | Tech Associate Mech. | C | 11 | 10 | 1 | 0 | SHORTFALL
36 | WTP/STP Chemist | C | 1 | 0 | 1 | 0 | SHORTFALL
37 | WTP Operator | C | 4 | 3 | 1 | 0 | SHORTFALL
38 | STP Operator | C | 3 | 2 | 1 | 0 | SHORTFALL
39 | WTP/STP Helper | C | 4 | 3 | 1 | 0 | SHORTFALL
40 | Engineer PM | D | 1 | 0 | 1 | 0 | SHORTFALL
41 | Sr Technician PM | D | 1 | 0 | 1 | 0 | SHORTFALL
42 | Solar Technician | D | 1 | 0 | 1 | 0 | SHORTFALL
43 | Supervisor (Fire) | E | 4 | 3 | 1 | 0 | SHORTFALL
44 | Painter | F | 6 | 5 | 1 | 0 | SHORTFALL
45 | Motor Technician | G | 2 | 1 | 1 | 0 | SHORTFALL
46 | Plumber L | H | 1 | 0 | 1 | 0 | SHORTFALL
47 | Driver (CLR Vehicles) | G | 10 | 9 | 1 | 0 | SHORTFALL
48 | Site Head (GM) | A | 1 | 1 | 0 | 0 | MATCHED
49 | HR Manager | A | 1 | 1 | 0 | 0 | MATCHED
50 | MIS Executive | A | 1 | 1 | 0 | 0 | MATCHED
51 | Fitter Mechanical | C | 1 | 1 | 0 | 0 | MATCHED
52 | Asst. Manager (Electrical) | D | 1 | 1 | 0 | 0 | MATCHED
53 | Fire Technician | E | 11 | 11 | 0 | 0 | MATCHED
54 | Welder | F | 1 | 1 | 0 | 0 | MATCHED
55 | Civil Fitter | F | 1 | 1 | 0 | 0 | MATCHED
56 | Stores Executive | F | 5 | 5 | 0 | 0 | MATCHED
57 | MT Supervisor | G | 1 | 1 | 0 | 0 | MATCHED
58 | Technician (HVAC) L | H | 1 | 1 | 0 | 0 | MATCHED
59 | Sr Electrician OPS | D | — | 1 | 0 | 1 | SURPLUS
60 | Boom Lift Operator | G | — | 3 | 0 | 3 | SURPLUS
61 | Technician | D | — | 3 | 0 | 3 | SURPLUS
| TOTAL |  | 281 | 159 | 129 | 7 | —

## 4_Phase1_172_Vacancies
PHASE-1 172 ROSTER — REQUIRED / FILLED / VACANT (CROSS-CHECKED)
Cross-check: Source Summary172 showed Vacant=82 because TRANSPORT vacant was typed as 7 (must be 10−4=6). Correct from Deployment172: Required 172 ¦ Filled 91 ¦ Vacant 81. All values are ≥ 0.
A. SECTION SUMMARY
Section | Required Count | Filled Count | Vacant | Fill % | Status
ADMIN | 8 | 3 | 5 | 38% | Low
CIVIL | 9 | 9 | 0 | 100% | Complete
ELV / SCADA | 10 | 0 | 10 | 0% | Critical
ELECTRICAL | 46 | 31 | 15 | 67% | On Track
MECHANICAL | 89 | 44 | 45 | 49% | Low
TRANSPORT | 10 | 4 | 6 | 40% | Low
TOTAL | 172 | 91 | 81 | 53% | —
B. DESIGNATION DETAIL — Required Count / Filled Count / Vacant Count
# | Section | Designation | Location / Area | Required Count | Filled Count | Vacant Count | Hiring Priority
1 | ELV / SCADA | Floor Technicians | PTB | 6 | 0 | 6 | CRITICAL
2 | ELV / SCADA | Supervisior | PTB | 2 | 0 | 2 | CRITICAL
3 | ELV / SCADA | Engineers | PTB | 1 | 0 | 1 | CRITICAL
4 | ELV / SCADA | Supervisior | Airside | 1 | 0 | 1 | CRITICAL
5 | ADMIN | HSE & Compliance Manager | ADMIN | 1 | 0 | 1 | CRITICAL
6 | ADMIN | Materials Manager | ADMIN | 1 | 0 | 1 | CRITICAL
7 | ADMIN | Sr. Manager (Civil) | ADMIN | 1 | 0 | 1 | CRITICAL
8 | ADMIN | Sr. Manager (Electrical) | ADMIN | 1 | 0 | 1 | CRITICAL
9 | ADMIN | Sr. Manager (Mechanical) | ADMIN | 1 | 0 | 1 | CRITICAL
10 | ELECTRICAL | MRSS Operators (Sr Technician) | MRSS | 4 | 0 | 4 | HIGH
11 | ELECTRICAL | Technicians (ELE -Ops) | Admin building | 4 | 0 | 4 | HIGH
12 | ELECTRICAL | Technicians (MST) | Airside | 4 | 0 | 4 | HIGH
13 | ELECTRICAL | Shift Engineers | Overall ALS | 2 | 0 | 2 | HIGH
14 | ELECTRICAL | Shift Engineers | PTB | 2 | 1 | 1 | LOW
15 | MECHANICAL | Sewerman & Drainage | ALS QRT | 6 | 0 | 6 | HIGH
16 | MECHANICAL | HVAC Sr Technicians (chiller plant) | Chiller plant | 4 | 0 | 4 | HIGH
17 | MECHANICAL | Pump operator | CFR Satellite | 4 | 0 | 4 | HIGH
18 | MECHANICAL | STP helper | STP | 4 | 0 | 4 | HIGH
19 | MECHANICAL | Sewage pump operator | ALS QRT | 4 | 0 | 4 | HIGH
20 | MECHANICAL | Helper Tech Associate Plu | Admin building | 3 | 0 | 3 | HIGH
21 | MECHANICAL | Plumbing -Tech | Admin building | 3 | 0 | 3 | HIGH
22 | MECHANICAL | Pump Operator | RO/firepump room | 3 | 0 | 3 | HIGH
23 | MECHANICAL | Technician-mech | ALS QRT | 4 | 1 | 3 | HIGH
24 | MECHANICAL | Helper Tech Associate Mech. | Admin building | 2 | 0 | 2 | HIGH
25 | MECHANICAL | Shift Engineers | AIRSIDE & Landside | 2 | 0 | 2 | HIGH
26 | MECHANICAL | Asst Manager | Overall | 1 | 0 | 1 | LOW
27 | MECHANICAL | STP incharge | WTP | 1 | 0 | 1 | LOW
28 | MECHANICAL | STP operator | STP | 4 | 3 | 1 | LOW
29 | MECHANICAL | Safety Officer | ALS QRT | 1 | 0 | 1 | LOW
30 | MECHANICAL | Shift Engineers | PTB | 1 | 0 | 1 | LOW
31 | MECHANICAL | WTP Helper | WTP | 2 | 1 | 1 | LOW
32 | MECHANICAL | WTP technician | WTP | 4 | 3 | 1 | LOW
33 | TRANSPORT | High raise machine operators 21mt& 18mt | TRANSPORT | 2 | 0 | 2 | MEDIUM
34 | TRANSPORT | Associate mgr/JM | TRANSPORT | 1 | 0 | 1 | LOW
35 | TRANSPORT | Mechanical Helper | TRANSPORT | 1 | 0 | 1 | LOW
36 | TRANSPORT | Paint machine operator | TRANSPORT | 1 | 0 | 1 | LOW
37 | TRANSPORT | Tyre Technician | TRANSPORT | 1 | 0 | 1 | LOW
38 | ADMIN | HR Manager | ADMIN | 1 | 1 | 0 | OK
39 | ADMIN | MIS Executive | Terminal | 1 | 1 | 0 | OK
40 | ADMIN | Site Head (GM) | ADMIN | 1 | 1 | 0 | OK
41 | ELECTRICAL | Asst Manager | Overall | 1 | 1 | 0 | OK
42 | ELECTRICAL | Floor Technicians | Terminal | 7 | 7 | 0 | OK
43 | ELECTRICAL | High Mast Operator (Technicians) | High Mast | 1 | 1 | 0 | OK
44 | ELECTRICAL | MRSS Operators (Technician) | MRSS | 1 | 1 | 0 | OK
45 | ELECTRICAL | MRSS Operators (Technician) | Terminal | 3 | 3 | 0 | OK
46 | ELECTRICAL | Ops Technicians (ELE -Ops) | AGL-EAST | 1 | 1 | 0 | OK
47 | ELECTRICAL | Ops Technicians (ELE -Ops) | AGL-WEST | 3 | 3 | 0 | OK
48 | ELECTRICAL | Sr Technicians | MRSS | 4 | 4 | 0 | OK
49 | ELECTRICAL | Substation Operators | AGL-EAST | 2 | 2 | 0 | OK
50 | ELECTRICAL | Substation Operators | Admin | 4 | 4 | 0 | OK
51 | ELECTRICAL | Substation Operators | Terminal | 1 | 1 | 0 | OK
52 | ELECTRICAL | Technicians | Landside | 2 | 2 | 0 | OK
53 | MECHANICAL | Fitter Mechanical | Utility | 1 | 1 | 0 | OK
54 | MECHANICAL | HVAC Floor Technicians | ADMIN | 1 | 1 | 0 | OK
55 | MECHANICAL | HVAC Floor Technicians | ATC | 1 | 1 | 0 | OK
56 | MECHANICAL | HVAC Floor Technicians | Admin | 1 | 1 | 0 | OK
57 | MECHANICAL | HVAC Floor Technicians | PTB | 3 | 3 | 0 | OK
58 | MECHANICAL | HVAC Floor Technicians | Utility | 2 | 2 | 0 | OK
59 | MECHANICAL | Helper (Tech-Ass-Mec) chiller plant | Utility | 2 | 2 | 0 | OK
60 | MECHANICAL | Helper Tech Associate Mech. | ADMIN/MRSS | 1 | 1 | 0 | OK
61 | MECHANICAL | Helper Tech Associate Mech. | ALS QRT | 4 | 4 | 0 | OK
62 | MECHANICAL | Helper Tech Associate Mech. | Utility | 2 | 2 | 0 | OK
63 | MECHANICAL | Helper Utility building | Airside | 1 | 1 | 0 | OK
64 | MECHANICAL | Plumbing Technican | ATC Pump House | 2 | 2 | 0 | OK
65 | MECHANICAL | Plumbing Technican | Admin | 2 | 2 | 0 | OK
66 | MECHANICAL | Plumbing Technican | CFR Pump House | 2 | 2 | 0 | OK
67 | MECHANICAL | Plumbing Technican | East Side | 1 | 1 | 0 | OK
68 | MECHANICAL | Plumbing Technican | PTB | 1 | 1 | 0 | OK
69 | MECHANICAL | Plumbing Technican | West Side | 2 | 2 | 0 | OK
70 | MECHANICAL | Pump Operator | Utility | 1 | 1 | 0 | OK
71 | MECHANICAL | Shift Engineers | Utility | 1 | 1 | 0 | OK
72 | MECHANICAL | Technician-mech | ATC | 1 | 1 | 0 | OK
73 | MECHANICAL | Technician-mech | PTB | 3 | 3 | 0 | OK
74 | MECHANICAL | Technician-mech | Utility | 1 | 1 | 0 | OK
75 | TRANSPORT | Motor Electrician | TRANSPORT | 1 | 1 | 0 | OK
76 | TRANSPORT | Motor Technician | TRANSPORT | 1 | 1 | 0 | OK
77 | TRANSPORT | Road sweeper operator | TRANSPORT | 2 | 2 | 0 | OK
78 | CIVIL | Carpenter | PTB | 1 | 1 | 0 | OK
79 | CIVIL | Civil Fitter | PTB | 1 | 1 | 0 | OK
80 | CIVIL | Civil Helper | Airside | 2 | 2 | 0 | OK
81 | CIVIL | Engr | PTB | 2 | 2 | 0 | OK
82 | CIVIL | Supervisor Civil | ALS | 1 | 1 | 0 | OK
83 | CIVIL | Supervisor Civil | PTB | 1 | 1 | 0 | OK
84 | CIVIL | Welder | PTB | 1 | 1 | 0 | OK
| TOTAL |  |  | 172 | 91 | 81
C. CROSS-CHECK
Deployment172: Required 172 ¦ Filled 91 ¦ Vacant 81. Vacant Count = Required Count − Filled Count (always ≥ 0). Section A unchanged.

## 5_TL_Action_Items
TEAM LEAD ACTION ITEMS & PRIORITY HIRING
TOP 10 SHORTFALLS vs FULL PLAN 281
Rank | Designation | Required | Filled | Gap
1 | Runway Team | 15 | 2 | 13
2 | HVAC Technician Mechanical | 21 | 11 | 10
3 | Civil Helper | 13 | 5 | 8
4 | Pump Operator | 9 | 1 | 8
5 | Shift Engineer (Electrical) | 8 | 1 | 7
6 | Sewerman & Drainage | 6 | 0 | 6
7 | Sr. Technician Ops | 11 | 6 | 5
8 | Desk Engineer (SCADA) | 4 | 0 | 4
9 | MST | 4 | 0 | 4
10 | Supervisor Civil | 7 | 3 | 4
RECOMMENDED ACTIONS
Priority | Action | Detail
P0 | Close Phase-1 ELV/SCADA (0/10) | No ELV names on roster — block go-live risk. Raise urgent hiring for 1 Engineer + 3 Supervisors + 6 Floor Technicians.
P0 | Fill Admin leadership gaps | Still open: Sr. Manager Mech/Elec/Civil, HSE & Compliance, Materials Manager (5 of 8 Admin).
P1 | Complete Phase-1 Mechanical vacancies | Largest vacant block in 172 roster (~45). Prioritize Pump Operators, Sewerman, STP/WTP, HVAC Sr Techs, Shift Engineers.
P1 | Electrical Shift Engineers & MST | Against 281: Shift Eng Elec gap 7, MST gap 4. Against 172: several Shift Eng / MST / Admin ELE-Ops still vacant.
P1 | Confirm Fire & Landside out of Ph-1 | Fire (17) and Landside (11) are in 281 but not in 172 — get TL/client written confirmation they are deferred.
P2 | Runway Team pipeline for later phase | Biggest 281 gap (−13). Do not pull focus from Ph-1 172 unless client escalates runway readiness.
P2 | Clean surplus designations | Boom Lift Operator (3), generic Technician (3), Sr Electrician OPS (1) are filled but not in 281 required list — remap or justify.
P2 | Keep dual tracking | Track (a) 172 Phase-1 fill % weekly and (b) 281 full-plan gap separately so numbers are not mixed in client updates.
STATUS SUMMARY LINES YOU CAN PASTE TO TL
• Full Plan: 281 required ¦ 159 available (141 deployed + 18 will join) ¦ Gap 122 (43%).
• Phase-1 Immediate: 172 required ¦ 91 named on roster (53%) ¦ 81 vacant (47%).
• Deferred beyond Phase-1: 109 positions.
• Critical open: ELV/SCADA 10/10 vacant; Admin leadership 5 open; Mechanical largest vacant volume.
• Top 281 gaps: Runway Team 13, HVAC Tech 10, Civil Helper 8, Pump Operator 8, Elec Shift Eng 7.

## 6_Data_Sources
DATA SOURCES & METHOD
Files used
File | Role
GMR_SUMMARY_MANPOWERSHEET.xlsx | Primary analysis workbook (DailySheet, DesignationSummary, Plan281, Deployment172, plan172, Summary172)
Phase-1 VOX Technical Deployment.xlsx | Original client Ph-1 details (172) and CLR quotation (281)
GMR.xlsx | Earlier site duty roster (source manpower names)
Phase-1_172_Manpower_Base_Roster.xlsx | Earlier generated 172 base roster template
Definitions
Term | Meaning
Required 281 | Total manpower in CLR quotation / Plan281 sheet
Required 172 | Immediate Phase-1 proposal (Admin8+Civil9+ELV10+Elec46+Mech89+TMT10)
Filled Now (159) | Count of people listed in DailySheet / DesignationSummary Filled Count
Deployed (141) | DailySheet remarks contain Deployed At Site
Will Join (18) | DailySheet remarks contain Will join
Phase-1 Named (91) | Deployment172 rows that have a Name filled
Phase-1 Vacant (81) | Deployment172 rows with Designation but empty Name
Gap vs 281 (122) | 281 − 159
Deferred (109) | 281 − 172
Note: Team mapping on Sheet 1 uses designation→team mapping from Plan281 structure. Surplus designations without a 281 required count (Boom Lift Operator, Technician, Sr Electrician OPS) are listed on Sheet 3 as SURPLUS.